## Assessment Details
Assessment Details
Security Classification | Confidential
Risk Assessment Title | Organization-wide initial risk assessment
Risk Assessment Scope | All business activities, locations and infrastructure are within scope
Context of Risk Assessment | As part of obtaining certification to the ISO27001 standard for information security, this risk assessment has been carried out to set a baseline for future work, and to identify the major risks the organization currently faces, particularly with regard to Internet-facing services
Risk Acceptance Criteria | Generally, all risks rated LOW will be accepted. The acceptance of risks rated MEDIUM is at the discretion of the risk owner and top management
Version | 1
Dated | 12 Dec 20XX
Risk Assessors | Lead Assessor - Jack Wilkinson
Risk Assessment Participants | CIO CISO Heads of department
Approval | Gaston Davide, CEO
Date Approved | 20 Dec 20XX
Asset-Based Risk Assessment and Treatment Tool
ISMS-FORM-06-1

## Risk Assessment
Asset-Based Risk Assessment and Treatment Tool
Start with your most valuable assets and the most likely threats that will cause the highest impact.
To refresh chart data on the risk dashboard, click on “Refresh All” on the Data ribbon.
| RISK DESCRIPTION | [6 empty] | PRE-TREATMENT ASSESSMENT | [6 empty] | TREATMENT PLAN | [7 empty] | POST-TREATMENT ASSESSMENT
| Ref | Asset Group | Asset | Threat | Vulnerability | Risk Type | Risk Owner | Existing Controls | Likelihood | Likelihood Rationale | Impact | Impact Rationale | Risk Score | Risk Level | Treatment Option Chosen | Proposed Treatment Action | Annex A/Control Reference | Treatment Cost | Treatment Action Owner | Treatment Action Timescale | Treatment Action Progress | Treatment Action Status | Post-Treatment Likelihood | Post-Treatment Likelihood Rationale | Post- Treatment Impact | Post-Treatment Impact Rationale | Post-Treatment Risk Score | Post-Treatment Risk Level | Comments
Herrrera | 1 | Red e informacion | Coneccion de la red e integridad de la informacion | Inyeccion de datos falsos, DOS | Movimiento lateral IT → OT a través del servidor Historian | IA | CISO | Monitoreo de la red | 2 | Con un monitoreo de la actividad en la red es poco probable que un atacante pueda realizar y mantener ese movimiento lateral | 5 | El atacante puede tener acceso a la red y a partir de ahi escalar hasta bloquear o vulnerar accesos, monitorear o robar informacion | 10 | MEDIUM | Share | Mantener actualizado los SO, implementar monitoreo sobre los sistemas criticos | A.8.20 Networks security | Medio | CISO | 2-4 meses | 0% | Not Started | 1 | Las probabilidades se reducen drasticamente al llevar una actualizacion de software y llevando un control y registro de la actividad dentro de la red | 5 |  | 5 | MEDIUM
Herrrera | 2 | Dispositivos OT | Integridad de los dispositivos | Modificacion del comportamiento de los dispositivos | Compromiso de cuentas administrativas del dominio con acceso a sistemas OT | IA | CISO | Control de cuentas con acceso | 3 | Si los usuarios no cuentan con una educacion sobre la seguridad de las cuentas, un atacante podria vulnerar facilmente los accesos, luego depende del control que se lleve en cuanto a politicas de acceso y autenticacion | 5 | Puede provocar comportamientos inesperados en dispositivos de control o produccion de la organizacion | 15 | HIGH | Share | Capacitacion a los usuarios con acceso y securizacion de autenticacion a travez de 2fa por ejemplo | A.8.2 Privileged access rights A.8.5 Secure authentication | Bajo | CISO | 6-9 meses | 0% | Not Started | 1 | Es muy poco probable que las cuentas se vulneren luego de implementar controles de acceso y medidas que aumente la seguridad y autenticidad de los accesos | 5 |  | 5 | MEDIUM
Guarnieri | 3 | Red | Network connections | Un atacante con acceso al segmento OT podría enviar comandos industriales no autorizados hacia los PLCs, modificando registros, parámetros de proceso o estados operativos. | Protocolos industriales sin autenticación ni cifrado (Modbus TCP / DNP3) | IA | OT / ICS Manager | Firewall perimetral general y acceso OT restringido, sin autenticación/cifrado específico en Modbus TCP / DNP3. | 4 | Si un atacante alcanza la red OT, puede enviar comandos a PLCs sin autenticación. | 5 | Puede alterar procesos físicos críticos y afectar seguridad/disponibilidad operacional. | 20 | HIGH | Modify | Restringir y monitorear tráfico Modbus TCP / DNP3 mediante firewall industrial, allowlisting, segmentación OT e inspección de comandos hacia PLCs. | IEC 62443-3-3 SR 1.2, SR 2.1, SR 3.1, SR 4.3, SR 5.1, SR 5.2 | Alto | OT / ICS Manager | 3-6 meses | 0% | Not Started | 3 | La segmentación, allowlisting e inspección industrial reducen la posibilidad de envío no autorizado de comandos a PLCs. | 2 | El impacto sigue siendo crítico si se logra modificar un proceso físico. | 6 | MEDIUM
Noguerón | 4 | OT | HMI | Alteracion maliciosa de upgrades-updates de SCADA para alterar operacion de planta via ataque de cadena de suministro | HMI con sistemas operativos EOL (End of Life) sin parches de seguridad | IA | CISO | Redes OT segmentadas | 2 | No hay muchos HMI en funcionamiento y no estan en lugares criticos | 4 | Paralizacion de la linea de producción | 8 | MEDIUM | Modify | Firewall OT |  | Alto | OT / ICS Manager | 3-6 meses | 0% | Not Started | 1 | Un control adicional normalmente muy efectivo | 4 | No se modifica | 4 | LOW
Noguerón | 5 | Red | VPN appliance | Interrupción de linea de producción | Acceso remoto de proveedores sin controles de seguridad adecuados | IA | CISO | Firewalls-Protecciones basicas de red | 2 | Proceso de Gestion de identidades maduro en la org | 4 | Paralizacion de la linea de producción | 8 | MEDIUM | Modify | Segundo factor de autenticacion |  | Medio | OT / ICS Manager | 3-6 meses | 0% | Not Started | 1 | Un control adicional normalmente muy efectivo | 4 | No se modifica | 4 | LOW
Guarnieri | 6 | Red | Network configurations | Un incidente originado en la red IT, como ransomware o compromiso de una estación de trabajo, podría propagarse hacia la red OT y afectar PLCs, HMIs o SCADA. | Ausencia de segmentación IT/OT (Modelo Purdue no implementado) | IA | CISO | Firewall perimetral y controles IT básicos, sin segmentación IT/OT ni DMZ industrial. | 5 | Un incidente IT puede alcanzar directamente activos OT. | 5 | Puede comprometer SCADA, HMIs, PLCs y detener la operación. | 25 | HIGH | Modify | Implementar segmentación IT/OT con DMZ industrial, firewalls dedicados, reglas de mínimo privilegio y allowlisting entre zonas. | IEC 62443-3-2; IEC 62443-3-3 SR 5.1, SR 5.2, SR 1.13, SR 7.6; IEC 62443-2-1 | Alto | CISO / OT Manager | 6-9 meses | 0% | Not Started | 2 | La separación IT/OT y la DMZ industrial reducen la propagación directa desde IT hacia OT. | 5 | Una afectación OT seguiría pudiendo detener operaciones críticas. | 10 | MEDIUM
Guarnieri | 7 | Infromación | Operations — Process and procedural documentation / operational process data | Un atacante podría alterar datos históricos o en tiempo real del proceso, generando reportes falsos hacia ERP, gerencia, auditoría o cumplimiento regulatorio. | Falta de protección de integridad sobre los datos del Historian, permitiendo manipulación silenciosa de registros operacionales sin modificar necesariamente el proceso físico real. | CI | CISO - OT data owner | Accesos generales y backups básicos del Historian, sin controles fuertes de integridad. | 4 | El Historian está conectado a OT y ERP, aumentando la superficie de ataque. | 4 | Datos falsificados pueden afectar decisiones, cumplimiento, trazabilidad y facturación. | 16 | HIGH | Modify | Asegurar la integridad del Historian con control de accesos, logging, monitoreo, backups protegidos, segregación y validación de datos hacia ERP. |  | Medio / Alto | OT Data Owner / Operations Manager | 4-6 meses | 0% | Not Started | 2 | Controles de acceso, logging, monitoreo y validación reducen la manipulación silenciosa del Historian. | 4 | Datos falsos pueden seguir afectando decisiones, cumplimiento y trazabilidad. | 8 | MEDIUM
[14 empty] | LOW |  |  | IEC 62443-3-3 SR 3.4, SR 6.1, SR 6.2, SR 7.3, SR 7.4, SR 4.1 | [10 empty] | LOW
[14 empty] | LOW | [13 empty] | LOW
[14 empty] | LOW | [13 empty] | LOW
[14 empty] | LOW | [13 empty] | LOW
[14 empty] | LOW | [13 empty] | LOW
[14 empty] | LOW | [13 empty] | LOW
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Dashboard
ISO/IEC 27001 Asset-based risk assessment and treatment tool dashboard
To refresh chart data on the risk dashboard, click on “Refresh All” on the Data ribbon.
Pre-treatment assessment
Post-treatment assessment
Classification of risk level | [7 empty] | Risk profile diagram
The chart below shows the rating scheme used to determine risk level based on a combination of likelihood and impact. | [7 empty] | The charts below show the spread of risk severities before and after risk treatment.
LIKELIHOOD: What are the chances of the risk event happening?
| IMPACT: How major could the consequences be if the risk event happened? | [6 empty] | Pre-treatment | [6 empty] | Post-treatment
|  | INSIGNIFICANT 1 | MINOR 2 | SIGNIFICANT 3 | MAJOR 4 | SEVERE 5 | Risk Likelihood | 5 | 0 | 0 | 0 | 0 | 1 | Risk Likelihood | 5 | 0 | 0 | 0 | 0 | 0
| ALMOST CERTAIN 5 | MEDIUM 5 | MEDIUM 10 | HIGH 15 | HIGH 20 | HIGH 25 |  | 4 | 0 | 0 | 0 | 1 | 1 |  | 4 | 0 | 0 | 0 | 0 | 0
| LIKELY 4 | LOW 4 | MEDIUM 8 | HIGH 12 | HIGH 16 | HIGH 20 |  | 3 | 0 | 0 | 0 | 0 | 1 |  | 3 | 0 | 1 | 0 | 0 | 0
| MODERATE 3 | LOW 3 | MEDIUM 6 | MEDIUM 9 | HIGH 12 | HIGH 15 |  | 2 | 0 | 0 | 0 | 2 | 1 |  | 2 | 0 | 0 | 0 | 1 | 1
| UNLIKELY 2 | LOW 2 | LOW 4 | MEDIUM 6 | MEDIUM 8 | MEDIUM 10 |  | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 2 | 2
| RARE 1 | LOW 1 | LOW 2 | LOW 3 | LOW 4 | MEDIUM 5 |  |  | 1 | 2 | 3 | 4 | 5 |  |  | 1 | 2 | 3 | 4 | 5
[8 empty] | Risk impact | [6 empty] | Risk impact
Treatment plan

## Pre-treatment risks (hidden)
Number of Pre-treatment risks by risk level
Risk level | Pre-treatment
Low | 6
Medium | 3
High | 4
Risk level | Pre-treatment
Low | 1
Medium | 2
High | 10

## Pre-treat risk levels by owner (hidden)
Pre-treatment risk levels by risk owner
Risk Level | Risk Owner | Risk Level
HIGH | CIO | 4
| Development Manager | 1
| CISO | 2
| COO | 2
| HR Manager | 1
MEDIUM | Supplier Manager | 1
| CISO | 1
LOW | Facilities Manager | 1

## Post-treatment risks (hidden)
Number of Post-mitigation risks by risk level
Risk level | Post-treatment
Low | 8
Medium | 5
High | 0
Risk level | Post-treatment
Low | 3
Medium | 10
High | 0

## Risks by risk level pre & post (hidden)
Number of risks by risk level pre and post treatment
Risk level | Pre-treatment | Post-treatment
Low | 6 | 8
Medium | 3 | 5
High | 4 | 0
Risk level | Pre-treatment | Post-treatment
Low | 1 | 3
Medium | 2 | 10
High | 10 | 0

## Treatment option chosen (hidden)
Risks by treatment option chosen
Treatment Option Chosen | Count of Asset Group
Modify | 10
Accept | 2
Avoid | 1

## Treatment cost (hidden)
Total treatment cost by risk level
Risk Level | Sum of Treatment Cost
LOW
MEDIUM | 12000
HIGH | 45500

## Treatment action owner (hidden)
Treatment action owner
Count of Treatment Action Owner | Risk Level
Treatment Action Owner | LOW | MEDIUM | HIGH
CIO |  |  | 4
Development Manager |  |  | 1
Supplier Manager |  | 1
CISO |  | 1 | 2
COO |  |  | 2
HR Manager |  |  | 1
(blank)

## Reference Controls
ISO/IEC 27001 Annex A Reference Controls
The following list of reference controls is used within the risk assessment worksheets.
REF
A.5 Organizational controls
A.5.1 Policies for information security
A.5.2 Information security roles and responsibilities
A.5.3 Segregation of duties
A.5.4 Management responsibilities
A.5.5 Contact with authorities
A.5.6 Contact with special interest groups
A.5.7 Threat intelligence
A.5.8 Information security in project management
A.5.9 Inventory of information and other associated assets
A.5.10 Acceptable use of information and other associated assets
A.5.11 Return of assets
A.5.12 Classification of information
A.5.13 Labelling of information
A.5.14 Information transfer
A.5.15 Access control
A.5.16 Identity management
A.5.17 Authentication information
A.5.18 Access rights
A.5.19 Information security in supplier relationships
A.5.20 Addressing information security within supplier agreements
A.5.21 Managing information security in the ICT supply chain
A.5.22 Monitoring, review and change management of supplier services
A.5.23 Information security for use of cloud services
A.5.24 Information security incident management planning and preparation
A.5.25 Assessment and decision on information security events
A.5.26 Response to information security incidents
A.5.27 Learning from information security incidents
A.5.28 Collection of evidence
A.5.29 Information security during disruption
A.5.30 ICT readiness for business continuity
A.5.31 Legal, statutory, regulatory and contractual requirements
A.5.32 Intellectual property rights
A.5.33 Protection of records
A.5.34 Privacy and protection of PII
A.5.35 Independent review of information security
A.5.36 Compliance with policies, rules and standards for information security
A.5.37 Documented operating procedures
A.6 People controls
A.6.1 Screening
A.6.2 Terms and conditions of employment
A.6.3 Information security awareness, education and training
A.6.4 Disciplinary process
A.6.5 Responsibilities after termination or change of employment
A.6.6 Confidentiality or non-disclosure agreements
A.6.7 Remote working
A.6.8 Information security event reporting
A.7 Physical controls
A.7.1 Physical security perimeters
A.7.2 Physical entry
A.7.3 Securing offices, rooms and facilities
A.7.4 Physical security monitoring
A.7.5 Protecting against physical and environmental threats
A.7.6 Working in secure areas
A.7.7 Clear desk and clear screen
A.7.8 Equipment siting and protection
A.7.9 Security of assets off-premises
A.7.10 Storage media
A.7.11 Supporting utilities
A.7.12 Cabling security
A.7.13 Equipment maintenance
A.7.14 Secure disposal or re-use of equipment
A.8 Technological controls
A.8.1 User endpoint devices
A.8.2 Privileged access rights
A.8.3 Information access restriction
A.8.4 Access to source code
A.8.5 Secure authentication
A.8.6 Capacity management
A.8.7 Protection against malware
A.8.8 Management of technical vulnerabilities
A.8.9 Configuration management
A.8.10 Information deletion
A.8.11 Data masking
A.8.12 Data leakage prevention
A.8.13 Information backup
A.8.14 Redundancy of information processing facilities
A.8.15 Logging
A.8.16 Monitoring activities
A.8.17 Clock synchronization
A.8.18 Use of privileged utility programs
A.8.19 Installation of software on operational systems
A.8.20 Networks security
A.8.21 Security of network services
A.8.22 Segregation of networks
A.8.23 Web filtering
A.8.24 Use of cryptography
A.8.25 Secure development life cycle
A.8.26 Application security requirements
A.8.27 Secure system architecture and engineering principles
A.8.28 Secure coding
A.8.29 Security testing in development and acceptance
A.8.30 Outsourced development
A.8.31 Separation of development, test and production environments
A.8.32 Change management
A.8.33 Test information
A.8.34 Protection of information systems during audit testing

## Example ATV Risks
Asset ¦ Threat ¦ Vulnerability ¦ Risk Type ¦ Control Examples
The following list shows a list of assets, with associated threats and vulnerabilities, risk type and the Annex A controls that might be used to treat them.
You may use this table to help to identify relevant risks for your organization and to define where the controls from Annex A of ISO/IEC 27001 are applicable.
REF | EXAMPLE ASSET GROUP | EXAMPLE THREAT(S) | EXAMPLE VULNERABILITY | RISK TYPE(S) | ANNEX A CONTROL
1 | Organization | It is not clear what the organization's rules are for managing information security. Employees and others aren't aware of what they should be doing to protect the organization | Policies either don't exist or don't cover the required areas | Availability | A.5.1 Policies for information security
2 | Organization | New threats have emerged that need to be addressed in policies | Policies are out of date, do not reflect the organization's business or technical setup | Confidentiality, Integrity and Availability | A.5.1 Policies for information security
3 | Organization | It is not clear who should be doing what with respect to information security | Roles and responsibilities for information security have not been clearly defined | Confidentiality | A.5.2 Information security roles and responsibilities
4 | Business activities | An individual is able to perform all of the steps required to perform a sensitive business process. Checks are insufficient to prevent accidental amendment or destruction of data | Processes have not been designed to limit the scope for deliberate or accidental actions | Confidentiality, Integrity and Availability | A.5.3 Segregation of duties
5 | Organization | The organization is unaware of their legal or regulatory responsibilities and may break the law without realising it | No contact is in place with bodies who may impose requirements on our organisation | Confidentiality and Availability | A.5.5 Contact with authorities
6 | Business activities | The organization lacks up to date knowledge of information security issues such as current threats, new controls and other relevant information | No budget is currently available for attendance at conferences, seminars and training events | Confidentiality, Integrity and Availability | A.5.6 Contact with special interest groups
7 | Organization | Information gathered and created during projects is not adequately protected | Project document stores are set up ad hoc and often outside of more formal access controls | Confidentiality | A.5.8 Information security in project management
8 | Information | Data held on mobile devices is prone to loss or theft of the device, or unauthorised access | No guidance is given to employees about how to protect their mobile devices | Confidentiality | A.8.1 User endpoint devices
9 | Physical/Site | A teleworking site does not meet the information security standards ensured at main locations and data is exposed to loss or theft | Teleworking arrangements are informal and no checking is done of the environment in place | Confidentiality | A.6.7 Remote working
10 | Business activities | It is not clear who does what with respect to cloud security and one party (e.g. cloud service customer) is under the impression that the other (e.g. cloud service provider) is monitoring a particular aspect | No split of responsibilities is agreed as part of the cloud take-on service | Availability | A.5.23 Information security for use of cloud services
11 | People | An employee is recruited who could deliberately breach information security | Employee references are not thoroughly checked and no additional background checks are mandated | Confidentiality and Availability | A.6.1 Screening
12 | People | It is not clear to employees what their responsibilities for information security are | Current employment contracts don't cover information security in sufficient detail | Availability | A.6.2 Terms and conditions of employment
13 | People | Employees do not follow security policies as they are regarded as irrelevant | Management do not enforce and emphasise the need to comply with information security policies | Confidentiality | A.5.4 Management responsibilities
14 | People | Employees and contractors are not aware of information security policies and are unable to spot potential breaches | Little information security awareness training is currently conducted, either as part of induction or ongoing employment | Confidentiality, Integrity and Availability | A.6.3 Information security awareness, education and training
15 | People | The consequences of committing an information security breach are not sufficiently clear to employees | Several recent high profile security breaches have not been followed up with disciplinary action | Confidentiality | A.6.4 Disciplinary process
16 | People | Ex-employees could breach information security after leaving e.g. making confidential information public | It is not made clear to leavers that they have continuing obligations for confidentiality after employment has ended | Confidentiality | A.6.5 Responsibilities after termination or change of employment
17 | Information | It is not clear what assets we are trying to protect and where they are located | Information is spread across many unmanaged data sets and their contents are uncertain | Confidentiality | A.5.9 Inventory of information and other associated assets
18 | Organization | No-one takes responsibility for protecting specific assets | There is a tendency to assume that someone else is protecting an asset | Integrity and Availability | A.5.9 Inventory of information and other associated assets
19 | Organization | Information and assets are used in ways that are not acceptable to the organization e.g. devices are physically abused and information left exposed | Employees are not told what actions are regarded as acceptable or unacceptable | Confidentiality | A.5.10 Acceptable use of information and other associated assets
20 | Hardware | Assets are not returned when someone leaves the organization | The leaver procedure doesn't currently cover the return of all assets | Integrity | A.5.11 Return of assets
21 | Information | Assets that are stored with a cloud service provider are not returned | System decommissioning processes are outdated and don't cover cloud services | Confidentiality | A.5.23 Information security for use of cloud services
22 | Information | It is not clear how specific items of information should be protected | The types of information that require specific protection have not been defined | Availability | A.5.12 Classification of information
23 | Information | Employees are unable to tell how information should be protected | Definitions of sensitivity are varied across departments; information which one department regards as sensitive is not well protected in another | Availability | A.5.13 Labelling of information
24 | Information | Assets are handled inappropriately due to a lack of definition of how they should be addressed | Procedures do not define the controls required according to the classification of the asset | Integrity | A.5.10 Acceptable use of information and other associated assets
25 | Hardware | Removable media is used without effective protection of the data held on it | Unencrypted memory sticks are routinely used as part of business processes, and for home working | Integrity | A.7.10 Storage media
26 | Information | The information stored on media is vulnerable to compromise when it is disposed of | Old computers are currently given to charity with just a factory reset | Availability | A.7.10 Storage media
27 | Information | Data held on media is not adequately protected whilst in transit e.g. by the use of encryption | Unencrypted backup tapes are sometimes left unattended in a vehicle during the transfer process | Confidentiality | A.7.10 Storage media
28 | Information | Employees or third parties have access to information without authorisation or by mistake | Access to some parts of the shared folder system is too loose for the types of information stored on it | Availability | A.5.15 Access control
29 | Network | A user could gain unauthorised access to information via a network that they have no reason to legitimately use | Guest Wi-Fi is connected to the main network without an adequate firewall in place | Confidentiality and Integrity | A.5.15 Access control
30 | Information | User accounts are created without authority or not removed when no longer needed | The user account creation process lacks sufficient oversight from management | Confidentiality, Integrity and Availability | A.5.16 Identity management
31 | Information | Users are given an inappropriate level of access within systems | Some user role definitions are too broad; more granular definitions are required | Confidentiality | A.5.18 Access rights
32 | Information | Privileged access rights could be used by an unauthorised person to breach information security | Some systems are not fully understood and so admin level access is often provided by default | Confidentiality, Integrity and Availability | A.8.2 Privileged access rights
33 | Information | User passwords are known to someone other than the user to whom they relate | The help desk procedure to issue password resets is not sufficiently secure | Confidentiality, Integrity and Availability | A.5.17 Authentication information
34 | Organization | Inappropriate levels of access remain in place long term and attempts to increase permissions are not spotted | People transferring between roles often retain the access they had in their previous role | Confidentiality | A.5.18 Access rights
35 | Information | Ex-users still have access even when they have left the organization | The process to disable leavers' user accounts takes too long | Confidentiality | A.5.18 Access rights
36 | People | Users share user accounts and let others know their passwords | Temporary employees are often told to use shared user accounts | Confidentiality | A.5.17 Authentication information
37 | Information | Too much access is allowed to a user where their role does not require it | Some systems only allow for either an admin or user level access, with no granularity of access available | Confidentiality | A.8.3 Information access restriction
38 | Information | Logon to secure systems is possible by unauthorised users | Some potentially sensitive HR information is available via a hyperlink without logging on | Confidentiality | A.8.5 Secure authentication
39 | Information | Users do not set appropriately-strong passwords | Many users choose to cycle round a few, known passwords | Confidentiality | A.5.17 Authentication information
40 | Information | A privileged utility program could be used to bypass security controls and gain unauthorised access to information | Database editing tools are generally used in development, and may be accessible outside that team | Availability | A.8.18 Use of privileged utility programs
41 | Information | Program source code could be destroyed or tampered with to benefit an attacker | Access to source code is not currently logged | Confidentiality and Availability | A.8.4 Access to source code
42 | Software | The use of encryption within the organization is haphazard and uncoordinated, resulting in a lack of effectiveness and possible illegal use | The encryption algorithms and the key lengths used are not always appropriate for the purpose | Availability | A.8.24 Use of cryptography
43 | Software | Cryptographic keys are often lost or compromised, potentially resulting in the loss of encrypted data | There are no guidelines, rules, or secure storage locations provided for cryptographic keys | Confidentiality | A.8.24 Use of cryptography
44 | Physical/Site | It is not clear where physical security has been, or needs to be, applied | Some locations are shared with other companies and physical separation is badly-defined | Availability | A.7.1 Physical security perimeters
45 | Physical/Site | Unauthorised people are able to bypass entry controls | Care of access cards in some locations is inadequate e.g. stored in unlocked drawers | Confidentiality and Availability | A.11.1.2 Physical entry controls
46 | Physical/Site | Unauthorised people are able to gain physical access to sensitive information | Some rooms which are used to discuss sensitive business issues, involving the use of whiteboards, are not sufficiently secured | Confidentiality and Availability | A.7.2 Physical entry
47 | Physical/Site | An accident, attack or natural disaster could destroy or severely affect sensitive information and its processing | A new chemical processing plant has been constructed near to the data centre | Confidentiality | A.7.5 Protecting against physical and environmental threats
48 | Physical/Site | People in secure areas leave the area open to attack or unauthorised access | No regular checks are made on how well secure areas are maintained | Confidentiality | A.7.6 Working in secure areas
49 | Physical/Site | Access could be gained to secure areas via a publicly-accessible delivery area | At some smaller locations, deliveries are made to within a secure office | Confidentiality | A.7.2 Physical entry
50 | Information | Screens showing sensitive information can be seen by unauthorised people | Some of the computer screens in HR point towards a glass partition with an employee rest area on the other side of it | Availability | A.7.8 Equipment siting and protection
51 | Physical/Site | Essential facilities are disabled due to a power outage | Power supply is variable at some locations, with regular disruptions | Confidentiality and Availability | A.7.11 Supporting utilities
52 | Network | Someone could listen in to sensitive information by tapping a cable | Some cables are routed along the outside of walls to which there is public access | Availability | A.7.12 Cabling security
53 | Physical/Site | Equipment often breaks down or fails to protect information due to a lack of appropriate care | Some of the equipment used for business-critical operations is old | Integrity and Availability | A.7.13 Equipment maintenance
54 | Hardware | Equipment, information or software is removed from a location without the knowledge or permission of the organization | No rules are in place about which equipment may be removed, and under what circumstances | Confidentiality, Integrity and Availability | A.7.10 Storage media
55 | Hardware | Assets containing sensitive information are left unprotected whilst offsite | Laptops are often taken to conferences, on planes and in hotel rooms | Confidentiality, Integrity and Availability | A.7.9 Security of assets off-premises
56 | Information | Sensitive information can be read from storage media that has been disposed of or reused | Devices with flash storage are not always wiped effectively when being disposed of | Availability | A.7.14 Secure disposal or re-use of equipment
57 | Information | Someone could access systems they are not authorised to using a device that has been left logged on | Employees often leave their desks for meetings, lunch and coffee breaks | Integrity | A.8.1 User endpoint devices
58 | Information | Support staff, e.g. cleaners and security personnel, are able to read sensitive information left unattended on desks | Work in progress is often left out overnight | Integrity | A.7.7 Clear desk and clear screen
59 | Business activities | Loss of data due to incorrect performance of operating procedures | Operating procedures are not clear to all employees who need to perform them and vary according to who does them | Confidentiality, Integrity and Availability | A.5.37 Documented operating procedures
60 | Business activities | Information security may become compromised when changes are made to the organization, business processes or information processing facilities and systems | Changes are managed informally, with little focus on information security | Integrity | A.8.32 Change management
61 | Hardware | Systems run slowly or not at all because the resources required are not available | Performance and capacity of resources such as storage and processors is not monitored | Confidentiality and Integrity | A.8.6 Capacity management
62 | Software | A poorly-tested software change results in errors in a business-critical process | Software changes made in development are put live without adequate testing or supervision | Confidentiality, Integrity and Availability | A.8.31 Separation of development, test and production environments
63 | Information | An administrator of a cloud service makes a serious and unrecoverable error that affects service availability or security | Inadequate control over admin functions that have the potential to disrupt operations if used incorrectly or inappropriately | Confidentiality | A.5.23 Information security for use of cloud services
64 | Information | Systems are affected by malware e.g. ransomware or spyware, having a serious effect on service delivery and security | The anti-malware program in use does not have a good reputation for effectiveness | Confidentiality, Integrity and Availability | A.8.7 Protection against malware
65 | Information | Data is lost and cannot be recovered from backup | It is not clear what backups are required or take place | Availability | A.8.13 Information backup
66 | Software | Suspicious events are not detected due to inadequate logs being kept | Logging is inconsistent and poorly configured in many areas of hardware and software | Confidentiality, Integrity and Availability | A.8.15 Logging
67 | Software | Incriminating logs are wiped or altered by an attacker | Logs are not subject to access controls and are not backed up | Confidentiality, Integrity and Availability | A.8.15 Logging
68 | Information | An insider with admin access views sensitive data | The activities of administrators and operators cannot be verified | Integrity | A.8.15 Logging
69 | Business activities | The time sequence of an attack cannot be identified because each of the clocks involved tell a different time | Clocks on systems are not synchronised | Confidentiality, Integrity and Availability | A.8.17 Clock synchronization
70 | Business activities | The organization can't tell if a cloud service has been compromised because no logs are kept | Little monitoring of cloud services is in place | Confidentiality, Integrity and Availability | A.5.23 Information security for use of cloud services
71 | Software | Software is installed on an operational system which causes an unwanted effect e.g. compatibility issues or the introduction of vulnerabilities | Installation of software is not subject to change control | Confidentiality | A.8.19 Installation of software on operational systems
72 | Software | A hacker exploits an undetected vulnerability and steals information | Vulnerabilities in systems are not identified or addressed and could be exploited by attackers | Confidentiality | A.8.8 Management of technical vulnerabilities
73 | Software | A user installs some software that introduces vulnerabilities to the organization and its network | Users regularly install downloaded software on to their computers and onto servers | Confidentiality | A.8.19 Installation of software on operational systems
74 | Organization | Penetration tests disrupt a live system during peak service hours | There is no coordination between the audit department and business operations | Confidentiality, Integrity and Availability | A.8.34 Protection of information systems during audit testing
75 | Network | An external threat actor is able to gain access to the network | Network devices and their configuration are unmanaged and uncoordinated, so introducing vulnerabilities for the organization | Confidentiality and Integrity | A.8.20 Networks security
76 | Network | The required security mechanisms, service levels and management requirements for network services are not agreed with the supplier and so are not provided | Contracts with suppliers are generally quite vague regarding the services provided | Integrity | A.8.21 Security of network services
77 | Network | An external threat actor is able to gain access to a less critical network, and then use this access to enter more business-critical networks | An attacker, having gained access to the network, is able to see and access all systems and devices | Confidentiality, Integrity and Availability | A.8.22 Segregation of networks
78 | Network | A hacker is able to exploit the weaknesses in virtual networking to carry out an attack | Virtual networks are configured differently to physical ones and as a consequence don't provide the same required level of security | Confidentiality, Integrity and Availability | A.8.20 Networks security
79 | Information | Information in transit is intercepted and compromised | It is not clear what controls should be applied to information in transit | Confidentiality, Integrity and Availability | A.5.14 Information transfer
80 | Information | Information in transit to and from third parties is intercepted and compromised | Transfer of information between the organization and external parties is not subject to adequate protection | Integrity | A.5.14 Information transfer
81 | Information | Confidential emails are intercepted and used as the basis for an attack e.g. fraudulent bank transfer | information sent in electronic messaging systems e.g. email and messenger services, is not protected | Confidentiality, Integrity and Availability | A.5.14 Information transfer
82 | Information | Confidential information is shared with others by a third party because it was not agreed that this is not allowed | Non-disclosure agreements are not routinely put in place | Integrity | A.6.6 Confidentiality or non-disclosure agreements
83 | Information | New or changed systems are open to attack in ways that could have been predicted | Information security is not considered adequately when new or enhanced systems are designed | Integrity | A.5.8 Information security in project management
84 | Information | Information involved in application services is intercepted and modified in order to commit fraud | The level of encryption used for application services is weak | Confidentiality, Integrity and Availability | A.8.26 Application security requirements
85 | Information | Application service transactions are used to mount an attack on the organization or its business partners | Application service transactions are open to amendment whilst in transit, with no indication that they have been altered | Confidentiality, Integrity and Availability | A.8.26 Application security requirements
86 | Software | Software is written that has an unacceptable level of vulnerabilities | No guidance is given to developers about how to write secure code | Confidentiality and Integrity | A.8.25 Secure development life cycle
87 | Software | Changes are uncontrolled whilst in development leading to poor quality software and badly-defined releases | No formal change controls procedures are used within the organization | Confidentiality and Integrity | A.8.32 Change management
88 | Software | Business critical applications are adversely affected when the underlying operating platform is changed | There is no coordination between the teams rolling out operating platform changes and the application support teams | Confidentiality, Integrity and Availability | A.8.32 Change management
89 | Software | Significant modifications to software packages introduce security vulnerabilities, functionality issues and support problems | There is a culture of making sometimes unnecessary changes to off the shelf packages, for limited business benefits | Confidentiality, Integrity and Availability | A.8.32 Change management
90 | Software | Systems are designed without adequate regard to, or knowledge of, information security | No guidance is given to system designers about how to create secure systems | Confidentiality, Integrity and Availability | A.8.27 Secure system architecture and engineering principles
91 | Software | Development environments are able to be accessed by unauthorised persons who could introduce code that makes future attacks easier | The development environment has inadequate access control | Confidentiality, Integrity and Availability | A.8.31 Separation of development, test and production environments
92 | Software | Code developed by an outsourcing provider may contain security flaws that are not discovered by the organization | There are few checks on how code is written by third parties | Confidentiality, Integrity and Availability | A.8.30 Outsourced development
93 | Software | Security functionality doesn't work correctly in live software | No testing is routinely carried out on the security aspects of new or changed systems | Confidentiality, Integrity and Availability | A.8.29 Security testing in development and acceptance
94 | Software | Newly-implemented systems don't work as intended | Insufficient time is allocated to checking systems before they go live | Confidentiality, Integrity and Availability | A.8.29 Security testing in development and acceptance
95 | Information | Test data doesn't identify issues with the software being tested and is itself of value to an attacker (e.g. if copied from live data) | Test data is out of date and unrepresentative of system usage. It is held in an unsecured area | Confidentiality, Integrity and Availability | A.8.33 Test information
96 | Organization | An attacker gains access to the organization's network using logon credentials obtained from a supplier who has legitimate access | Little is known about the security controls that suppliers have in place | Confidentiality, Integrity and Availability | A.5.19 Information security in supplier relationships
97 | Organization | A supplier, who provides services to and has access to the organization's information, has inadequate security controls in place and suffers a breach involving the organization's data | No contractual requirements are specified that suppliers must meet in the area of information security | Confidentiality, Integrity and Availability | A.5.20 Addressing information security within supplier agreements
98 | Organization | A supplier uses contractors who do not have adequate security controls in place | We are generally unaware of whether suppliers use subcontractors, and if they do, who they are | Confidentiality, Integrity and Availability | A.5.21 Managing information security in the ICT supply chain
99 | Organization | A supplier is not delivering the level of service that they should | No statistics are collected or reported on regarding the levels of service provided by suppliers | Confidentiality, Integrity and Availability | A.5.22 Monitoring, review and change management of supplier services
100 | Organization | A supplier e.g. cloud service provider, makes a change that is not expected and which significantly affects the organization's business processes | Although we are informed of changes, we don't generally take notice of these as part of our change management process | Confidentiality, Integrity and Availability | A.5.22 Monitoring, review and change management of supplier services
101 | Information | It is not clear who should do what when an information security incident occurs | Responsibilities for information security incidents are not defined and no-one knows what to do if one is detected | Confidentiality, Integrity and Availability | A.5.24 Information security incident management planning and preparation
102 | Information | Management is not aware that an information security event has been detected | Events are happening all the time, but we don't have a way to bring them to the right person's attention | Availability | A.6.8 Information security event reporting
103 | Information | Weaknesses in information security do not get addressed because they are not reported | No-one has been asked to tell us if they become aware of a potential security issue | Confidentiality, Integrity and Availability | A.6.8 Information security event reporting
104 | Information | No decisions are taken about whether events should be escalated to incidents | We don't have an effective way to assess whether an event, or collection of events, represents an incident or not | Integrity | A.5.25 Assessment and decision on information security events
105 | Information | The response to information security incidents is inadequate and procedures are not used | There is no plan for what to do if a serious incident occurs | Confidentiality, Integrity and Availability | A.5.26 Response to information security incidents
106 | Information | Nothing is learned from incidents and no improvements are made | We tend to suffer the same types of incidents time after time | Confidentiality, Integrity and Availability | A.5.27 Learning from information security incidents
107 | Information | No usable or admissible evidence is collected as a result of a lack of awareness of how this must be done. Because of this, nobody can be prosecuted | No-one knows how to preserve or collect evidence in a form that would be admissible in court | Integrity | A.5.28 Collection of evidence
108 | Business activities | It is not known what level of information security must be provided during a disruptive event | Business continuity planning generally has little input from information security | Confidentiality, Integrity and Availability | A.5.29 Information security during disruption
109 | Business activities | Information security controls become ineffective when a disruptive event happens | Some of the business continuity plans in place involve using facilities with few controls available, compared to normal operation | Confidentiality, Integrity and Availability | A.5.29 Information security during disruption
110 | Business activities | The intended information security controls don't work during a disruptive event because they have never been tested | Information security controls are not routinely tested as part of business continuity tests | Confidentiality, Integrity and Availability | A.5.29 Information security during disruption
111 | Business activities | Information processing facilities fail due to a lack of sufficient redundancy | The level of availability required from systems is often not defined | Availability | A.8.14 Redundancy of information processing facilities
112 | Organization | It is not known what legislative, regulatory and contractual requirements each information system must meet and, as a result, such requirements are not met | There is no procedure or resourcing to understand what legal, regulatory and contractual requirements we should be meeting | Integrity | A.5.31 Legal, statutory, regulatory and contractual requirements
113 | Organization | The organization is subject to legal action as a result of breaching intellectual property rights and licensing requirements | People in the business are generally not aware about copyright laws and what we should be doing to stay within them | Integrity | A.5.32 Intellectual property rights
114 | Organization | Records that are required to be kept are lost, falsified or accessed, resulting in legal or contractual issues | There is no definition of the records that should be retained, how long for, and how they should be protected | Confidentiality | A.5.33 Protection of records
115 | Organization | Laws requiring the protection of personally identifiable information are breached, resulting in prosecution and fines | The organization's processing of PII does not always meet legal requirements | Confidentiality | A.5.34 Privacy and protection of PII
116 | Organization | Cryptography is used inappropriately, resulting in prosecution | There is little understanding of what may, and may not, be done in the area of cryptography | Confidentiality | A.5.31 Legal, statutory, regulatory and contractual requirements
117 | Organization | The implementation of information security is never independently checked and many controls do not work as intended | Although controls are theoretically in place, many aspects of the business have changed and the controls have not been changed with them | Confidentiality, Integrity and Availability | A.5.35 Independent review of information security
118 | People | Management does not check that policies and procedures are being followed and people stop using them over time | Policies are not generally available and little re-enforcement of their messages is routinely given | Confidentiality | A.5.36 Compliance with policies, rules and standards for information security
119 | Information | As systems evolve, security controls become less effective and more vulnerable to attack | Operating platforms are regularly being updated, but little attention is paid to whether the changes affect security | Integrity | A.5.36 Compliance with policies, rules and standards for information security

## Example Threats
Examples of Threats
The following is a standard list of typical threats that may be use as guidance for your risk assessment.
THREAT CATEGORY | THREAT | EXAMPLE
Human | Malicious outsider | Someone launches a denial of service attack on your cloud service platform
| Malicious insider | An employee or trusted third party accesses cardholder data in an unauthorised manner from inside your network
| Loss of key personnel | One or more people with key skills or knowledge are unavailable perhaps due to extended sickness
| Human error | An employee accidentally deletes cardholder data
| Accidental loss | A manager loses a memory stick with cardholder data on it
Natural | Fire | Your data centre burns down due to an electrical fault
| Flood | The nearby river breaks its banks and your main office is severely flooded
| Severe weather | Non-one can get into the office due to the weather
| Earthquake | The area of your main data centre is affected by an earth tremor that damages all your servers
| Lightning | All your servers are fried by a lightning strike on the data centre building
Technical | Hardware failure | A key physical server has a processor failure
| Software failure | Your financial system processes invoices incorrectly due to a bug
| Virus/Malicious code | A virus spreads throughout your network preventing access to your (and your customers') data
Physical | Sabotage | A disgruntled ex-employee takes an axe to your server room
| Theft | You come in on Monday morning to find some important drives have been stolen
| Arson | Someone with a grudge against your organisation starts a fire during the night
Environmental | Hazardous waste | A lorry carrying hazardous waste has an accident outside your office
| Power failure | The sub-station supplying your area has a meltdown
| Gas supply failure | There is a suspected leak and all supplies are turned off
Operational | Process error | Your new data transfer procedure doesn't cater for unexpected circumstances and cardholder data is lost or sent to the wrong destination
| Crime scene | A crime happens in or near your office and the area is sealed off by police

## Example Assets
Examples of Assets
The following is an initial list of typical assets that may be use as guidance for your risk assessment.
Note: information assets should be captured in more detail in the Information Asset Inventory.
ASSET GROUP | SUB-CATEGORY | ASSET
Business activities |  | Business-critical activities
Supporting activities
Compliance
Information | Cloud customer data | Personally identifiable information (PII)
Non-PII
| Corporate | Budgets
Sales forecasts
Corporate plans
Corporate policies
| Sales and Marketing | Customer records - names, addresses, contacts
Customer credit card information
Customer bank details e.g. Direct Debits
Website information
Customer preferences and purchase history
Customer correspondence and complaints
| Human Resources | Employee records - address, DOB, insurance numbers
Employee expense claims
Payroll information, including bank details
Training records
Recruitment information
Security clearance/check information
Employee complaints/disciplinary records
Sickness/occupational health records
Employment contracts
| Finance | Accounting records - invoices, bills, accounts
Business account banking details
| Buying | Supplier contact details
Buying plans
Commercial terms
| Legal | Supplier contracts
Customer contracts
Property leases
Credit agreements
Insurance policies
| Operations | Documents held on behalf of customers
Product specifications and bills of materials
Process and procedural documentation
Intellectual Property specific to the organisation
Resource plans
| Audit and Compliance | Internal audit records
External audit reports
Risk assessments
Software |  | Email
Accounting
Payroll
Bespoke software
Intranet
Website
Design
Office applications
Marketing
Industry-specific applications
Hardware |  | Computer servers
Networking equipment
Personal Computers
Mobile devices e.g. tablets
Mobile/Smart phones
Network |  | Network connections
Network devices
Network configurations
Physical/Site |  | Buildings
Server rooms, including air conditioning and power units
Machinery
Stock
Vehicles
Gas supply
Water
Network services
Telephone services
People | Key resources | Owner/Chief Executive
Managers
Engineers
Knowledge holders
Organization |  | Management
Structure
Project
Suppliers
Other |  | Other

## Likelihood
Likelihood
This table should be used to decide upon the most appropriate likelihood for a particular threat.
LIKELIHOOD | DESCRIPTION | SUMMARY
1 | Improbable | Has never happened before and there is no reason to think it is any more likely now
2 | Unlikely | There is a possibility that it could happen, but it probably won't
3 | Likely | On balance, the risk is more likely to happen than not
4 | Very Likely | It would be a surprise if the risk did not occur either based on past frequency or current circumstances
5 | Almost certain | Either already happens regularly or there is some reason to believe it is virtually imminent

## Impact
Impact
This table should be used as guidance to help to decide upon the correct impact rating for a particular threat.
IMPACT LEVEL |  | IMPACT AREAS
Impact rating | General description | Effect on customers | Financial cost | Health and Safety | Damage to reputation | Legal, Contractual and Organizational Compliance
1 | Negligible | No effect | Very little or none | Very small additional risk | Negligible | No implications
2 | Slight | Some local disturbance to normal business operations | Some | Within acceptable limits | Slight | Small risk of not meeting compliance
3 | Moderate | Can still deliver product/service with some difficulty | Unwelcome but could be borne | Elevated risk requiring immediate attention | Moderate | In definite danger of operating illegally
4 | High | Business is crippled in key areas | Severe effect on income and/or profit | Significant danger to life | High | Operating illegally in some areas
5 | Very High | Out of business; no service to customers | Crippling; the organisation will go out of business | Real or strong potential loss of life | Very High | Severe fines and possible imprisonment of staff

## Selection Tables (hidden)
Selection Tables
ONE TO FIVE | OPTIONS
Select… | Select…
1 | Accept
2 | Avoid
3 | Modify
4 | Share
5
RISK TYPE | TREATMENT ACTION STATUS
Select… | Select…
C | Not Started
I | In Progress
A | Completed
CI | Rejected
CA
IA
CIA

## Pivot tables (hidden)
Pivot Tables
Risk Type Table
Count of Risk Level | Column Labels
Row Labels | HIGH | MEDIUM | LOW | Grand Total
C | 4 | 1 |  | 5
A | 2 |  |  | 2
CIA | 4 | 1 | 1 | 6
Grand Total | 10 | 2 | 1 | 13
Risk Owner Table
Count of Risk Level | Column Labels
Row Labels | HIGH | MEDIUM | LOW | Grand Total
CIO | 4 |  |  | 4
Development Manager | 1 |  |  | 1
Supplier Manager |  | 1 |  | 1
CISO | 2 | 1 |  | 3
Facilities Manager |  |  | 1 | 1
COO | 2 |  |  | 2
HR Manager | 1 |  |  | 1
Grand Total | 10 | 2 | 1 | 13
Treatment Option Table
Row Labels
Modify
Accept
Avoid
Grand Total
Risks: Pre and Post Treatment
Risk level | Pre-Treatment | Post-Treatment
Low | 6 | 8
Medium | 3 | 5
High | 4 | 0
Treatment Cost Table
Row Labels | Sum of Treatment Cost
HIGH | 45500
MEDIUM | 12000
LOW
Grand Total | 57500